## Func Reqs
Num | Functional Req | Description | MoSCoW | Difficulty/Time
1 | Multiplayer | Users are able to play in turns with other users | Must | High
2 | Web Browser Accessible | Users are able to access the the game lobby from their web browser | Should | Medium
3 | Game is Complete / Playable | Users are able to play a full version of the game | Must | Very High
4 | Single Player Mode | Users can play single player (versus computer AI) | Won't | Very High
5 | Movement | Units should be able to move (with varying movement distances) correctly | Must | High
6 | Unit behaviour | Units are able to use unique moves | Must | High
7 | Tutorial / Help | Users can learn and understand the rules and mechanics and how the units interact | Must | Medium
8 | Matchmaking | Users can host and join a game session | Must | Low
9 | Gamification | Appropriate gamification mechanics should be implemented such that there is still an educational purpose | Must | High
10 | Challenge | The game should be offer enough challenge to invoke critical thinking | Must | Medium
11 | Account Registration | Users are able to register and login (with safe password hashing and authentication) | Could | Medium
12 | Save Profile | Users profiles are saved (and earned achievements integrated with MySQL) | Could | Medium
13 | Achievements | Users are able to earn achievements from progress | Could | Low
14 | Score / Leaderboard | Users can see their score vs other players | Should | Low
Num | Non - Functional Requirement | Description | MoSCoW | Difficulty/Time
15 | Availability | The application should be accessible on tablet browsers | Could | High
16 | Ease of use | The application should be easy to learn and understand | Should | High
17 | Accessibility | The application should be compliant with the WCAG guidelines, including good contrast and colour-blind friendly | Should | Low
18 | Security | The application should be playable in a secure session | Should | Low
19 | Factually Correct | The application should be factually correct in any cyber security concepts explored | Must | Low
20 | Performance / Latency | As a web browser game, it should be relatively smooth to both play and load (with quick multiplayer response times) | Must | High
21 | Scalability | The application should be scalable to the number of the players wanting to play at any given time | Should | Low
22 | Understanding | Users can learn deeper cyber security principles and trends whilst having fun | Must | High
23 | Fun to use | The application has a depth of mechanics and dynamics that lead to meaningful play | Must | High
24 | Flexbility for expansion | The application has different scenarios, moves, units as well as further game mechanics | Won't | High
25 | Feedback | The application offers custom feedback based on how they perform (similar to Chess) | Could | Very High
26 | Music | The application has good music that fits the theme / aesthetics | Should | High
27 | Animations | The application has good movement & ability animations | Should | High

## Non Func Reqs
Functional Req | Description | MoSCoW | Difficulty
Multiplayer | Users are able to play in turns with other users | Must | High
Web Browser Accessible | Users are able to access the the game lobby from their web browser | Should | Medium
Game is Complete / Playable | Users are able to play a full version of the game | Must | Very High
Account Registration | Users are able to register and login (with safe password hashing and authentication) | Could | Medium
Save Profile | Users profiles are saved (and earned achievements integrated with MySQL) | Could | Medium
Achievements | Users are able to earn achievements from progress | Should | Low
Score / Leaderboard | Users can see their score vs other players | Should | Low
Single Player Mode | Users can play single player (versus computer AI) | Won't | Very High
Non - Functional Requirement | Description
Availability | The application should be accessible on both desktop web browsers and via mobile tablets
Ease of use | The application should be easy to learn and understand
Accessibility | The application should cater for disabilities such as colour blindness
Security | The application should be secure and protect user’s credentials should account registration be implemented
Factually Correct | The application should be factually correct in any cyber security concepts explored
Performance / Latency | As a web browser game, it should be relatively smooth to both play and load (with quick multiplayer response times). However, latency is less of an issue given the turn-based mechanic.
Scalability | Should be able to deal with 2-4 connected users per game

## Remaining Work
Task / Requirement | MoSCoW | Difficulty
Establish Multiplayer Networking | Must | High
Web Browser Accessible | Should | Medium
Logic for Turn Based Movement | Must | Medium
Add Graphics / Sound Assets | Must | Low
Add Cyber Attack / Defence Items | Must | Low
Add Objectives / Goals | Must | Low
Add Minigame Tiles / Rounds | Should | High
Add a Score / Leaderboard | Should | Low
Account Registration | Could | Medium
Save Profile | Could | Medium
Add Achievements | Could | Low
Test the Application | Must | High
Complete the Application Sufficient for Review | Must | Very High
Obtain Feedback / Research Effectivity of Product | Should | Medium
Single Player Mode (with AI for computer) | Won’t | Very High

## User Stories
Refined User Stories based on User Requirements
ID | As a/an (role/user) | I want (functionality or feature) | So that (benefit) | MoSCoW | Req | Difficulty
1 | General Player | To view a units health and defence stats | I can determine how to act | Must | 22 | Low
2 | General Player | To view an abilities range, damage, cost and effect | I can determine how to act | Must | 22 | Low
3 | General Player | To view a colour-blind friendly UI | I can interact with the application easily | Should | 17 | Low
4 | General Player | To view a unit's movement range | I can determine how to act | Must | 2021-05-16 | Medium
5 | General Player | To view a unit's ability attack range | I can determine how to act | Must | 2021-06-16 | Medium
6 | General Player | To move a unit | I can attack a target | Must | 2021-03-05 | High
7 | General Player | To attack a target | I can kill an enemy unit | Must | 2021-03-06 | Medium
8 | General Player | To disable the target | I can stop them from moving | Must | 2021-03-06 | Medium
9 | General Player | To defend an ally unit | I can prevent them from dying | Must | 2021-03-06 | Medium
10 | General Player | Click on a move description | I can learn more about the attack nature and it's ability | Must | 2021-03-06 | Low
11 | General Player | Click on a unit | I can learn more about the attack vector and their responsibility | Must | 2021-03-06 | Low
12 | General Player | Click on and view a history log | I can keep up with the game's sequence of events | Should | 7 | Low
13 | General Player | Click on a unit map | I can see how units relate within a web application environment | Could | 16, 22 | High
14 | General Player | Be able to view the units remaining | I know what units I can select that can still move | Should | 16 | Low
15 | General Player | Be able to pan the camera and/or zoom in | I can see the map and units more clearly and from different angles | Could | 16 | Medium
16 | General Player | To view unique attack/defence animations for each mechanic | I can differentiate abilities - leading to meaningful play | Could | 27 | Very High
17 | General Player | A varied depth of mechanics and moves | I am interested in meaningful play | Could | 23, 24 | High
18 | General Player | An intermediate tutorial | I can quickly learn how to play | Should | 7
19 | General Player | A help bar | I can be reminded how to play | Should | 2021-07-16 | Medium
20 | General Player | Multiplayer functionality | I can host/join a session | Must | 1 | Very High
21 | General Player | Singleplayer functionality | I can play by myself | Won't | 4 | N/A
22 | General Player | To quit / leave the session | I can play with a friend | Must | 3 | Low
23 | General Player | To be able to to win / lose | so that the game has an end purpose | Must | 3 | Low
24 | Security Consultant | To be able to host a workshop session on multiple devices (iPads, Desktops) | I can organise fun and challenging training workshops | Could | 2021-02-15 | High
25 | Student | To learn about the OWASP #10 | I can learn more about the most popular attacks and mitigations for them | Must | 22 | Low
26 | General Player | Purchase & upgrade new units and abilities | I have a deeper reason to keep playing | Could | 24 | Very High
27 | General Player | To register an account and login | I can view and save my unlocked units | Could | 2021-11-12 | High

## Product Backlog
User Story | Description | MoSCoW Priority | Display | Sprint | Completion Time (Hours) | Fib Number
Mmm possibly not needed?
9 | Show the result of the calculations | Must | N/A | 1 | 0.75 | 1
12 | Display Threshold Indicators | Must | Top-Down | 1 | 1.5 | 2
12 | Display Displaced Thresholds | Must | Top-Down | 1 | 1.5 | 2
12 | Display Stopway/Clearway for both ends of the runway | Must | Top-Down | 1 | 2.25 | 3
12 | Display obstacle | Must | Top-Down | 1 | 2.25 | 3
12 | Display offset caused by RESA | Must | Top-Down | 1 | 1.5 | 2
4,12 | Display Centre Line | Must | Top-Down | 1 | 0.75 | 1
4,12 | Display Runway Strip | Must | Top-Down | 1 | 0.75 | 1
8 | Display Original Calculations | Should | Top-Down | 1 | 1.5 | 2
12 | Display arrow showing indication of take-off/ landing | Should | Top-Down | 1 | 1.5 | 2
12 | Display distance parts | Must | Top-Down | 1 | 3.75 | 5
13 | Choose from pre-existing obstacles | Must | Top-Down | 1 | 6 | 8
14 | Add a new obstacle to runway | Must | Top-Down | 1 | 2.25 | 3
26 | Zoom Views | Could | Top-Down | 1 | 3.75 | 5
12 | Implement input boxes for Obstacle Position | Must | N/A | 1 | 1.5 | 2
12 | Implement input box for current CAA Requirements | Must | N/A | 1 | 1.5 | 2
12 | Calculate Landing Distance Available when Landing Towards the object | Must | N/A | 1 | 2.25 | 3
12 | Calculate TORA for Take-off Away from an Obstacle | Must | N/A | 1 | 1.5 | 2
12 | Calculate TODA for Take-off Away from an Obstacle | Must | N/A | 1 | 1.5 | 2
12 | Calculate ASDA for Take-off Away from an Obstacle | Must | N/A | 1 | 1.5 | 2
12 | Implement Input for Engine Blast Allowance | Must | N/A | 1 | 0.75 | 1
12 | Test Cases for Calculations | Must | N/A | 1 | 6 | 8
1,2 | Test Cases for Runway Manipulation (Adding/Editing/Removing) | Should | N/A | 1 | 3.75 | 5
12 | Test Cases for User Input Correctness | Must | N/A | 1 | 2.25 | 3
3 | Settings to switch on autosave configurations | Must | N/A | 2
3 | Settings to switch off autosave configurations | Must | N/A | 2
16 | Export XML files | Should | N/A | 2
16 | Import XML files | Should | N/A | 2
16 | Implement buttons for exporting XML files | Should | N/A | 2
16 | Implement buttons for importing XML files | Should | N/A | 2
1 | Adjust runway lengths | Should | N/A | 2
2 | Add new runways to configuration | Should | N/A | 2
2 | Remove runways from configuration | Should | N/A | 2
5 | Display Obstruction Height/Scale | Must | Side-On | 2
12 | Display Threshold Indicators | Must | Side-On | 2
12 | Display Displaced Thresholds | Must | Side-On | 2
12 | Display Stopway/Clearway for both ends of the runway | Must | Side-On | 2
12 | Display obstacle | Must | Side-On | 2
12 | Display offset caused by RESA | Must | Side-On | 2
12 | Display slope angles | Must | Side-On | 2
5,12 | Display Runway Strip | Must | Side-On | 2
12 | Display arrow showing indication of take-off/ landing | Must | Side-On | 2
12 | Display distance parts | Must | Side-On | 2
13 | Choose from pre-existing obstacles | Must | Side-On | 2
14 | Add a new obstacle | Must | Side-On | 2
14 | Remove an obstacle | Must | Side-On | 2
15 | Edit pre-existing obstacles | Should | Side-On | 2
20 | Display TOCS/ALS slopes | Must | Side-On | 2
26 | Zoom Views | Could | Side-On | 2
26 | Pan Views | Could | Side-On | 2
14 | Remove an obstacle | Must | Top-Down | 2
15 | Edit pre-existing obstacles | Should | Top-Down | 2
19 | Display clear and graded areas | Must | Top-Down | 2
3 | Save configurations | Must | Top-Down | 2
25 | Implement buttons for exporting | Could | Top-Down | 2
26 | Pan Views | Could | Top-Down | 2
12 | Calculate Landing Distance Available when Landing over the object | Must | N/A | 2
12 | Calculate TORA/TODA/ASDA for Take-off Towards an Obstacle | Must | N/A | 2
21 | Select different runways/thresholds | Must | Both | 2
17 | Indicate direction of lowest threshold | Must | Both | 2
2020-12-15 | Test Cases for Object Manipulation (Adding/Editing/Removing) | Must | Both | 2
16 | Test Cases for File Importing/Exporting | Should | N/A | 2
3 | Test Cases for Saving/Loading States | Must | Both | 2
24 | Display for colour blind | Could | Top-Down | 3
10 | Create screen to show the maths behind the calculations | Must | N/A | 3
24 | Settings to change the display for colour blindness | Could | N/A | 3
11 | Optimise tool to be quick | Should | N/A | 3
25 | Research into Exporting JPEG, PNG, GIF | Could | N/A | 3
6 | Display Runway Side/Top Simultaneously | Must | Both | 3
22 | Display notifications | Must | Both | 3
6 | Rotate Between Side-On/Top-Down | Must | Both | 3
8 | Display Original Calculations | Must | Side-On | 3
24 | Display for colour blind | Could | Side-On | 3
7,12 | Display New Re-Declarations | Must | Side-On | 3
3 | Save configurations | Must | Side-On | 3
25 | Implement buttons for exporting | Could | Side-On | 3
25 | Export current view | Could | Side-On | 3
26 | Implement buttons for printing | Could | Side-On | 3
7,12 | Display New Re-Declarations | Must | Top-Down | 3
25 | Export current view | Could | Top-Down | 3
26 | Implement buttons for printing | Could | Top-Down | 3
29 | Implement option to change text size | Could | N/A | 3